## Product Backlog
|  | Name | StudentNo
|  | James Shaw | 17848280
|  | John Vos | 17806554
ID | User Story / Task / Deliverable | Priority | Planned Sprint | Actual Sprint | Total Effort Estimate | Total Actual Effort | Complete? | Issues / Log
1 | Current solution Review | must | 1 | 1 | 30 | 27 | Y | This is an important task as it informs what needs to be done later on. This went smoothly and while there was some debate over what we should keep and what we shouldn’t, we had allowed for this in our time estimate
2 | Overall Testing and Acceptance Checking | must | 1-6 | 1-6 | 78 | 79 | Y | Overall testing showed some minor issues which were then quickly fixed by the relevant dev team
3 | Research Specs for System Hardware Storage & Build | must | 1 | 1 | 16 | 20 | Y | Took longer to decide on hosting options than expected
4 | Data Collection | must | 2 | 2 | 29 | 34 | Y | This was a tedious task as there was a lot of data to collect for each subject area. Took a little longer than expected
5 | Database Design | must | 2 | 2 | 29 | 27 | Y | This was a fairly easy task, and took less time than anticipated
6 | Website Interface Design | must | 3 | 3 | 33 | 33 | Y | The interface for the website was developped with all users in mind and we used a template for each page to speed up the process
7 | Website Structure Design | must | 3 | 3 | 33 | 34 | Y | The basic structure for each page was the same so the design of these did not take too long. There was a small change made to one of the pages to ensure accessability but this was a minor change
8 | Website Interface Implementation | must | 4 | 4 | 31 | 28 | Y | No issues found here, implementation went smoothly and was completed quicker than expected
9 | Website Structure Implementation | must | 4 | 4 | 31 | 33 | Y | Upon implementation of the website pages, we decided to change the structure a little bit. This was based on some testing that found that the website wasn’t particularly easy to navigate, so some changes were made to the navigation system
10 | Database Implementation | must | 5 | 5 | 32 | 33 | Y | The database went down on Wednesday 12th so our database team spent an hour sorting this problem before starting with implementing our database on this day
11 | Staff Profile Page | Should | 5 | 5 | 32 | 33 | Y | A bug was found in the back end scripting that meant that some edge case data that should be accepted was throwing an error. This was a simple fix that only added an extra hour to development on this day
12 | Staff Account | Should | 6 | 6 | 32 | 32 | Y | Small change was made to the account page interface but as we were running ahead of schedule, this did not slow overall development
13 | Staff Login | Should | 6 | 6 | 32 | 33 | Y | Ensuring secure login took longer than expected
14 | File Uploads | Should | 7 | 7 | 32 | 30 | Y | No issues found here, managed to implement this quicker than expected
15 | File Downloads | could | 7 | 7 | 32 | 32 | Y | Getting the actual file download script to work took a little longer to implement than expected but we had managed to finish the implementation of the interface early
16 | Enquiry Forms | could | 8 | 8 | 20 | 18 | Y | Some small changes made to the Computer Science enquiry form
17 | Enquire Submission | could | 8 | 8 | 20 | 20 | Y | No issues in the development of this, back end team and database team worked effectively to get this running smoothly
18 | Responding to enquiries | could | 8 | 8 | 24 | 26 | Y | Took a couple hours longer than expected to change the account page due to debate over how this section should be presented but managed to make up time later on
People/Teams | Responsibilities
Dev Team | This refers to all the different dev teams as a whole - all working together
ScrumMaster | This is the project manager - they decide what happens in each sprint and ensures everyone is on task
Product Owner | This is the owner of the product - in this case, Brightmouth University
Website Dev Team | This is the team responsible for the front end development of the website. This would be the HTML, CSS and any Javascript
Back End Team | This is the team that is responsible for the server side scripting and management of the server. They would be using a language such as PHP
Database Team | This is the team responsible for the database creation and for writing any SQL scripting

## Sprint Backlog 1
Sprint 1 | 15/10/18 - 26/10/18 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Current Solution Review | 2.1. Review current prospectus pages for Computer Science | Must | Dev Team | Dev Team | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 2.2 Review current prospectus pages for Digital Development | Must | Dev Team | Dev Team | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 2.3. Review current prospectus pages for Business & Computing | Must | Dev Team | Dev Team | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 2.4. Come up with a list of things we like and don’t like about the current prospectus layout | Must | Dev Team | Dev Team | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.5. Decide on what we want to keep or change from the current design | Must | Dev Team | Dev Team | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.6. Create a list of what needs doing and when | Must | Dev Team | Dev Team | 8 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5
3. Research Specsifications for System Hardware requirements | 3.1 Research different hosting options | Must | Dev Team | Dev Team | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 8
| 3.2 Decide on the best hosting option based on the system requirements | Must | Website Dev Team | Website Dev Team | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 6
| 3.3 Buy a domain for the website | Must | Website Dev Team | Website Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 3.4 Choose a host for our site | Must | Website Dev Team | Website Dev Team | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
| 3.5 Create file structure on the server for the website files and organise any existing files into this. | Must | Back End / Website Dev Team | Back End / Website Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
4. Overall Testing & Acceptance Checking | 4.1 Check all course libraries are present and information is correct | Must | Product Owner | Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8
| 4.2 Test website host domain and functionality | Must | Website Dev Team | Website Dev Team | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| 4.3 Team meeting to discuss next steps | Must | ScrumMaster / Team | ScrumMaster / Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Ideal - remaining work effort in Ideal hours |  |  |  |  | 70 | 63 | 56 | 49 | 42 | 35 | 28 | 21 | 14 | 7 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 70 | 62 | 56 | 48 | 40 | 35 | 30 | 24 | 15 | 7 | 1

## Sprint Backlog 2
Sprint 2 | 29/10/18 - 10/11/18 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Database Design | 2.1. Write test Cases | Must | Database Dev Team | Database Dev Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2. Design database for computer science | Must | Database Dev Team | Database Dev Team | 9 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.3. Design database for digital development | Must | Database Dev Team | Database Dev Team | 9 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.4. Design database for business & computing | Must | Database Dev Team | Database Dev Team | 9 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.5. Test databases for all courses | Must | Database Dev Team | Database Dev Team | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2
3. Data Collection | 3.1. Write test Cases | Must | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 3.2. Collect data for computer science | Must | Dev Team | Dev Team | 9 | 0 | 0 | 0 | 0 | 5 | 7 | 0 | 0 | 0 | 0 | 12
| 3.3. Collect data for digital development | Must | Dev Team | Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 9
| 3.4. Collect data for business & computing | Must | Dev Team | Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 10
| 3.4. Test that all data has been collected | Must | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
4. Overall Testing & Acceptance Checking | 4.1. Test all databases have been designed. | Must | Dev Team / Scrum Master | Dev Team / Scrum Master | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 7
| 4.2. Test that all data has been collected for all courses. | Must | Dev Team / Scrum Master | Dev Team / Scrum Master | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 63 | 55 | 47 | 39 | 31 | 23 | 15 | 5 | -3

## Sprint Backlog 3
Sprint 3 | 21/11/18 - 23/11/18 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Website Structure Design | 2.1. Write test Cases | Must | Website Dev Team | Website Dev Team | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2. Design website structure for computer science | Must | Website Dev Team | Website Dev Team | 9 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11
| 2.3.Design website structure for digital development | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 9
| 2.4.Design website structure for business & computing | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 9
| 2.5. Test structure of website | Must | Website Dev Team | Website Dev Team | 4 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4
2. Website Interface Design | 3.1. Write test Cases | Must | Website Dev Team | Website Dev Team | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| 3.2. Design website interface for computer science | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 9
| 3.3. Design website interface for digital development | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 9
| 3.4. Design website interface for business & computing | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 9
| 3.5 Test website interface for all courses. | Must | Website Dev Team | Website Dev Team | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
4. Overall Testing & Acceptance Checking | 4.1 Ensure that all pages are covered | Must | Website Dev Team / Scrum Master | Dev Team / Scrum Master | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| 4.2 Ensure that accessability has been considered in the design | Must | Website Dev Team / Scrum Master | Website Dev Team / Scrum Master | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 65 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | -3

## Sprint Backlog 4
Sprint 4 | 26/11/18 - 07/12/18 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Website Interface Implementation | 2.1. Write test Cases | Must | Website Dev Team | Website Dev Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2. Implement website interface for computer science | Must | Website Dev Team | Website Dev Team | 9 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
| 2.3. Implement website interface for digital development | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.4. Implement website interface for business & computing | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 7
| 2.5 Test website interface for all courses. | Must | Website Dev Team / Scrum Master | Website Dev Team / Scrum Master | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3
3. Website Structure Implementation | 3.1. Write test cases | Must | Website Dev Team | Website Dev Team | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 3.2. Implement website structure for computer science | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 0 | 1 | 10
| 3.3 Implement website structure for digital development | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 0 | 0.5 | 9.5
| 3.4. Implement website structure for business & computing | Must | Website Dev Team | Website Dev Team | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 | 0.5 | 9.5
| 3.5. Test structure of website | Must | Website Dev Team / Scrum Master | Website Dev Team / Scrum Master | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
4. Overall Testing & Acceptance Checking | 4.1 Test that the interface works as expected | Must | Website Dev Team / Scrum Master | Website Dev Team / Scrum Master | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5
| 4.2 Test that the website is easy to use for someone who isn't very computer oriented | Must | Website Dev Team / Scrum Master | Website Dev Team / Scrum Master | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 49 | 43 | 35 | 27 | 19 | 11 | 1

## Sprint Backlog 5
Sprint 5 | 10/12/18 - 21/12/18 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Database Implementation | 2.1. Write test Cases | Must | Database Dev Team | DatabaseDev Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2 Implement database for Computer Science | Must | Database Dev Team | DatabaseDev Team | 10 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| 2.3 Implement Database for Digital Development | Must | Database Dev Team | DatabaseDev Team | 10 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 11
| 2.4. Implement database for business & computing | Must | Database Dev Team | DatabaseDev Team | 10 | 0 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 10
| 2.5. Test that the database has all the correct datatypes and sizes | Must | Database Dev Team / Scrum Master | Database Dev Team / Scrum Master | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
3. Staff Profile Page | 3.1. Write test cases | Should | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 3.2. Design Staff Profile page | Should | Website Dev Team | Website Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 10
| 3.3 Implement Staff Profile Page | Should | Website Dev Team | Website Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 10
| 3.4. Write back end scripting to allow the user to see their information from the database | Should | Back End/Database Dev Team | Back End/Database Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 1 | 11
| 3.5. Test the interface for functionality and test the database connection | Should | Back End / Database / Website Dev Team | Back End / Database / Website Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
4. Overall Testing & Acceptance Checking | 4.1 Test that data can be inserted and retrieved from the database | Must | Back End/Database Dev Team | Back End/Database Dev Team | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| 4.2 Test that all the correct data has been inserted into the database | Must | Database Dev Team | Database Dev Team | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| 4.3 Test that the profile page looks and behaves as expected |  | Website Dev Team | Website Dev Team | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 55 | 47 | 39 | 31 | 23 | 15 | 7 | -3

## Sprint Backlog 6
Sprint 6 | 31/12/18 - 11/01/18 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Staff Account | 2.1. Write test Cases | Should | Dev Team | Dev Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2. Design Staff Account interface | Should | Website Dev team | Website Dev Team | 10 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| 2.3. Implement Staff Account interface | Should | Website Dev team | Website Dev Team | 10 | 0 | 0 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 9
| 2.4 Design and implement the staff account in the database | Should | Database Dev Team | Database Dev Team | 10 | 0 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 10
| 2.5. Test that the interface is user friendly and easy to understand | Should | Website Dev team | Website Dev Team | 1 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 2
3. Staff Login | 3.1. Write test Cases | Should | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 3.2. Design staff login page | Should | Website Dev team | Website Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 10
| 3.3. Implement staff profile page | Should | Website Dev team | Website Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 10
| 3.4. Write back end scripting to allow the user to log in | Should | Database / Back End Dev Team | Database / Back End Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 11
| 3.5 Test website interface for functionality and test database connection | Should | Database / Website Dev Team | Database / Website Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
4. Overall Testing & Acceptance Checking | 4.1 Ensure that the login works and redirects users to the correct profile page and that the user has access to functionality such as 'forgotten password' and can change log in details if needed | Must | Dev Team | Dev Team | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
| 4.2 ensure that the correct information is displayed on the profile pages and that the user can change/add/remove information from their profile | Must | Dev Team | Dev Team | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 63 | 56 | 50 | 40 | 32 | 24 | 16 | 8 | -1

## Sprint Backlog 7
Sprint 7 | 14/01/19 - 25/01/19 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. File Uploads | 2.1. Write test Cases | Should | Dev Team | Dev Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2. Design file upload interface | Should | Website Dev Team | Website Dev Team | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
| 2.3. Implement file upload interface |  | Website Dev Team | Website Dev Team | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| 2.4. Write back end scripting to allow the user to upload files to the server | Should | Database Dev Team | Database Dev Team | 8 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
| 2.5 Test the interface of the uploads page to make sure its easy to use | Should | Website Dev Team | Website Dev Team | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3
| 2.6. Test that files are successfully uploading to the database | Should | Dev Team | Dev Team | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2
3. File Downloads | 3.1. Write test cases | Should | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 3.2. Design file download interface | Should | Website Dev Team | Website Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 10
| 3.3. Implement file download interface | Should | Website Dev Team | Website Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 8
| 3.4. Write back end code to fetch file from the file location on ther server and download it to the users computer | Should | Back End/Database Dev Team | Back End/Database Dev Team | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 0 | 12
| 3.5. Test that files can be downloaded | Should | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
4. Overall Testing & Acceptance Checking | 4.1 Test that files can be uploaded to the server. Test with a range of file types and sizes | Must | Dev Team / Scrum Master | Dev Team / Scrum Master | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
| 4.2 Test that files can be downloaded from the server. Test with a range of file types and sizes | Must | Dev Team / Scrum Master | Dev Team / Scrum Master | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 47 | 42 | 34 | 26 | 18 | 10 | 2

## Sprint Backlog 8
Sprint 8 | 28/01/19 - 08/02/19 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priority | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Dev Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Enquiry Form | 2.1. Write test Cases | Could | Website Dev Team | Website Dev Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2. Design enquiry form for Computer Science | Could | Website Dev Team | Website Dev Team | 6 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| 2.3. Design enquiry form for Digital Development | Could | Website Dev Team | Website Dev Team | 6 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| 2.4. Design enquiry form for Business & Computing | Could | Website Dev Team | Website Dev Team | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 2.5. Test all enquiry forms have correct data fields | Could | Website Dev Team | Website Dev Team | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3. Enquiry Submission | 3.1. Write test Cases | Could | Back End/Website Dev Team | Back End/Website Dev Team | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 3.2. Implement enquiry form for Computer Science | Could | Back End/Website Dev Team | Back End/Website Dev Team | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 6
| 3.3. Implement enquiry form for Digital Development | Could | Back End/Website Dev Team | Back End/Website Dev Team | 6 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 6
| 3.4. Implement enquiry form for Business & Computing | Could | Back End/Website Dev Team | Back End/Website Dev Team | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
| 3.5 Test that submissions work and upload correctly to the database | Could | Back End/Website Dev Team | Back End/Website Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
4. Responding to enquiries | 4.1 write test cases | Could | Dev Team | Dev Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.1 Edit the staff profile page so that they can view all enquiries related to the subject they teach or any general enquiries about university | Could | Database/Website Dev Team | Database/Website Dev Team | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 9
| 4.2 Ensure that the enquiry form includes a contact field so that members of staff can contact the individual to respond to their query | Could | Website Dev Team | Website Dev Team | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7
| 4.3 Ensure that staff can remove queries from the database once they have been dealt with so that each query is only responded to once | Could | Database/Website Dev Team | Database/Website Dev Team | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 7
| 4.5 Test functionality of query response system |  | Database/Website Dev Team | Database/Website Dev Team | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
5. Overall Testing & Acceptance Checking | 5.1 Test that the form is accepting the correct data and is uploading successfully to the database | Must | Dev Team / Scrum Master | Dev Team / Scrum Master | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
| 5.2 use edge cases to test any ristictions placed on any of the fields - eg date formatting or maximum field length | Must | Dev Team / Scrum Master | Dev Team / Scrum Master | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
Ideal - remaining work effort in Ideal hours |  |  |  |  | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Actual - remaining effort in Ideal hours |  |  |  |  | 80 | 72 | 67 | 59 | 50 | 42 | 34 | 26 | 18 | 10 | 0